## GBI-Monitoring Prj Changes
Srno | Request/Type of change | Requested date | Processed date | delay | Dependency | impact | comments | ownership

## Task-Issue-Risk Log
# | Item Description | Item Source | Type | Assigned to (If Applicable) | Status | Due Date (If Applicable) | Date Opened | Last Update | Date Closed | Closing Remarks | Notes | Comments
1 | AssetDB Redesign & Enhancements | Scope | Action Item | Muthu | In Progress | 2017-08-09 | 2017-07-31 | 2017-08-07 |  |  | In process of moving the Asset DB data to hbase It has been moved to hive tables. While loading into hbase tables, tried hostname as rowkey, its not accepting duplicates on hostname.Working on fixing the same.
2 | Cluster configurations | Scope | Action Item | Muthu | Yet to Start | 2017-08-09 | 2017-07-31 | 2017-08-07 |  |  | working on the script |  | Anurag | Open | Daily Meeting
3 | Moving the data, jobs feeding Atlas reports to ARA | Scope | Action Item | Srinjoy | In Progress | 2017-07-31 |  | 2017-08-07 |  |  | The data lying in DS needs to be moved to ARA The jobs that are running in DS should be ported to ARA Jobs is deployed in ARA servers . Need to be started by Gopal. |  | Basant | In Progress | Weekly Meeting
4 | Moving Lens1 jobs and data to ARA | Scope | Action Item | Muthu | In Progress | 2017-08-11 | 2017-07-17 | 2017-08-07 |  |  | Copying the data from DS to ARA |  | Sandeep | Closed | Scope
5 | Install python 2.7.10 in ARA cluster | Scope | Action Item | Muthu | Closed | [5 empty] | Placed python 2.7.10 in /ngs/app/edwroptp/anaconda/bin Installed happybase, cx_Oracle , kafka-python packages |  | Gopal | Pending Clarification | Discussion
6 | cluster diagnostics related task Need to get details from Gopal / Srini | Scope | Action Item | Muthu | Open | 2017-08-03 |  | 2017-08-07 |  |  | Will start working on this once current task is completed |  | Hareesh | Yet to Start | Action Item
7 | HDFS Movement related task Need to get details from Gopal / Srini | Scope | Action Item | MUthu | Open | 2017-08-03 |  | 2017-08-07 |  |  | Will start working on this once current task is completed |  | Anjana | N/A | Clarification
8 | Oxpecker data replication steps to be provided by Monitoring/Hadoop Operations team | Scope | Action Item | Muthu | Open | 2017-08-03 |  | 2017-08-07 |  |  | Will start working on this once current task is completed |  | Muthu |  | Issue
9 | End to end setup, validation of data flow from HBase to SOLR via Lily, testing with some sample SOLR queries. | Scope | Action Item | Muthu | Open | 2017-08-09 | 2017-07-19 | 2017-08-07 |  |  | Able to create indexer , not able to view the data in query page. Working on the same. |  | Srinjoy
10 | OpenTSDB installation in ARA | Scope | Action Item | Sujitha | In Progress |  |  | 2017-07-30 |  |  | OpenTSDB is not supported by DBA. need to develop a playbook to do this.Currently we don’t have any. Also, if it is a one time activity, our host don’t have internet access in which case we need to place the dependencies in apple conf, we usually reach out to SE LINUX Team for such activities. |  | Sujitha
11 | UI Prototype (Hbase – Lily - Solr ) Epic & Lens1 data to be indexed and searchable. |  |  | Bharath |  |  | 2017-08-08 | 2017-08-08 |  |  | 1) Ability to search for node/MR job/ Oozie Job Ids. 2) Ability to display anomalies at node and job level. 3) DAG View - Some Notes on Diagnosis Tool - One Live Page with a search button & the below content - Live DAG Tree with data and alerts - Anomalies with ability to drill-down based on metrics groups - ETA - Some visualization that conveys the message "WFxx supposed to start at 9Am, but started at 9:10AM and expected to finish by 12:30AM and is delayed/faster by 30 minutes" - Compare with previous runs, with default metrics comparison view with ability to drag and drop additional metrics - Exception Info - Cluster Health & Issues ( - Job/Workflow Health & Issues - Node (related to job) Health & Issues - Recommendations to Improve performance (lens-ii to begin with) - what if analysis - are there other rogue jobs that can be brought to the attention that can be killed - are there any task attempts that can be restarted to avoid slow data nodes - <more?> * In this approach, if we consider cascading delays like an S2F job impacting and F2C and that impacts 2 other Semantics and 4 other replication/export jobs, things will be more complex & ideal but requires a richer mapping of autosys jobs to various semantic, f2c, s2f, replication and some other custom jobs....and all of them to Hadoop jobs & workflows etc...At the least we should be able to predict the fate at workflow level where we have historical data. ETLP is another source that we should keep in consideration, which we may need if we need to get to process dependencies across modules (like F2C on a Semantic etc). But there is no guarantee that “all" jobs have entry there. | 1) Autosys job definitions ( Anjana to setup seed data in a hbase table ) 2) Anomaly Detection Service 3) Lens1 to Lens2 integration for realtime data | Bharath
12 | REST API to load data from Autosys definitions | [5 empty] | 2017-07-28 | 2017-08-01 |  |  |  | 8/1: completed on local. Deployment issues in ARA. 7/31:Anjana-was having issues with base connection to ARA. Built API on local. Need this connection issue to be resolved to proceed further Ron testing | Tejaswar
13 | -- Anomalies with ability to drill-down based on metrics groups -- Job/Workflow Health & Issues --Node (related to job) Health & Issues | [5 empty] | 2017-07-28 | 2017-08-04 |  |  | 8/7: The Webapp API code is not establishing a stable connection to the hbase in ARA; that is the issue I'm working on as of now. 8/4: Tomcat is Setup and webapp code which works locally is added to it; | REST API to load data from anomaly detection service | Harish M
14 | Compare with previous runs, with default metrics comparison view with ability to drag and drop additional metrics | [5 empty] | 2017-07-28 | 2017-08-07 |  |  | 8/7: The Webapp API code is not establishing a stable connection to the hbase in ARA; that is the issue I'm working on as of now. 8/4: Tomcat is Setup and webapp code which works locally is added to it; | REST API to load job metrics data | Vidya
15 | Autosys Job Definitions API |  |  | Anjana |  |  | 2017-07-28 | 2017-08-01 |  |  | 8/1: API built on local; deployment issues 7/26: decided to build API by ourselves 7/25: on ORDS liecensing - checking with roopak jain/evgeny gamaley/sanjay Kumar Working on API to read data from Autosys data source. |  | Srini
16 | UDM / Autosys python script from api to hbase |  |  | Anjana | Closed |  |  | 2017-08-01 | 2017-08-01 | Completed | completed on 08/01 |  | Santhosh
17 | UDM/Autosys push to Kafka queue |  |  | Anjana | In progress | [7 empty] | Praveen
18 | Automating API from HBase to UI | [9 empty] | built one function which takes input as table name and iterates for all the columns within to give out the data |  | Karthik
19 | DAO/Cache layer to load node to rack mapping | [5 empty] | 2017-07-19 | 2017-08-09 |  |  |  |  | Bharath
20 | 360 DAG View |  |  | Karthik |  |  | 2017-07-17 | 2017-08-09
21 | Interactive Query |  |  | Bharath |  |  | 2017-08-08 | 2017-08-09 |  |  | Compare with previous runs, with default metrics comparison view with ability to drag and drop additional metrics
22 | Exception Info |  |  | Anjana |  |  | 2017-07-26 | 2017-08-09 |  |  | Data Collection | 08/09: Still awaiting inputs from Splunk team - Splunk DBA team will work towards providing us the resolution 1) Job level exceptions -- Lens2 2) Service level exceptions -- Splunk - meeting postponed to July 26th 1)Hadoop Service level exceptions via splunk forwarder 2)Job level exceptions ( Lens2? ) 3) Task attempt logs. 8/1:meeting setup with Amay for 8/2 on splunk exception info
23 | Hbase CRUD Ops |  |  |  | closed |  | 2017-07-31 | 2017-08-08 | 2017-08-08 | Completed
24 | OpenTSDB CRUD Ops |  |  |  | In progress |  | 2017-07-31 | 2017-08-07 |  |  |  | 8/7: Bharath will be investigating on the CRUD operations for OpenTSDB. 7/31: Writing to OpenTSDB in monsoondev cluster was done using native TSD API, The other operations are yet to be explored
25 | Data Source & Model Plug & Play |  |  | Hareesh | [7 empty] | Batch processing Real-time
26 | Anomaly Detection Service |  |  | Hareesh | [7 empty] | Infra metrics Job Metrics Hadoop Service Metrics -- NN RPC Queue utilisation metrics Job Counters - Recommendations to Improve performance (lens-ii to begin with) - what if analysis - are there other rogue jobs that can be brought to the attention that can be killed - are there any task attempts that can be restarted to avoid slow data nodes Generic Roll-up of anomalies to higher level view -- ex: roll-up node level anomalies to rack level
27 | Data Pipeline
28 | New Job API a.k.a realtime view of jobs & constituent containers state |  |  | Gopal | [7 empty] | Following options are available: 1) Define Splunk forwarders for Application Master logs and publish the events to Kafka for realtime consumption 2) Poll RM URLs periodically , this is totally inefficient as full response would have to be downloaded and reprocessed. Its also inefficient as a single call would return the result only for a single task attempt. RM - Realtime Job Status API
29 | New Job API - Extract the data from RM/AM REST API |  |  | Gopal | [7 empty] | 1) Identify the AM's HTTP port by parsing AM log 2) Connect to AM directly for all requests thereafter.
30 | Data Collection API- 1.framework around multiple sources that would get data in Dataframe. - done 2.Push the data frame to hbase/opentsdb - connector need to be merged to api 3)push data in son format to kafka queue - done 4)Design Kafka queues 5)rowkey design for epic - done 6)check if multiple sources can be accessed in parallel 7)Dynamic queue creation - done 8)parameterize the variables 9)test on ARA cluster/packaging |  |  | Anjana | [7 empty] | 7/25: removed dependencies for pyspark from the API for now to avoid cluster level dependencies on python packages. Did write Kafka producer in python alone. Sill have issues with package version in ARA cluster for e.g.:requests package in Anaconda. Besides that, able to create a queue and publish cooked up data into the queue. Need to merge base connector after base package has been installed and discuss Kafka queue structure with Hareesh which he will let me know by EOD. 7/24: As discussed with Srini and goal in the scrum call, we are pushing the data to base even before pushing to Kafka hence no need to write a separate consumer. 7/23: working prototype of pushing data from multiple sources to Kafka queue. Need to write consumer logic and merge it to the automated framework and then push into base/opentsdb. Run this in ARA/monsoon. On ARA I need default python to be anaconda/v2.7 .. no access to edit bashrc file.
31 | Correlation API & UI Display (RCA) |  |  | Hareesh | Yet to Start
32 | Overall Working prototype •RCA Tool •Miss SLA •Data Pipeline |  |  | Gopal | Yet to Start
33 | Historical SLA miss data correlated with Cluster performance, Job profile changes and resource allocation. |  |  | Hareesh | Yet to Start
34 | Splunk data collection |  |  | Anjana | In Progress |  | 2017-07-31 | 2017-08-09 |  |  |  | 8/1:meeting setup with Amay. will have an ETA tomorrow 7/31: After meeting with Amay we finalized on using spunk forwarders to fork the data to ARA Kafka queue. I did send the priorities and list of data sources to Amay on 31/7. Besides hfs_audit rest of all we requested for only exception info
35 | Splunk data collection - HDFS Audit Log |  |  | Anjana | In Progress
36 | UX-UI |  |  | Vidya | In Progress |  | 2017-08-07 | 2017-08-09
37 | Espresso |  |  | Harish M | In Progress |  | 2017-07-31 | 2017-08-04 |  |  |  | 8/3: Mailed Sandeep regarding the steps for onboarding as customer to the web service tool. 8/1: Espresso WebService API (find & getTicketDetails operations) states the usage of the Espresso Web Service API needs to be registered as consumer in the tool. I came across this around EOD I'm yet to explore this aspect.
38 | CST |  |  | Harish M | closed |  |  | 2017-08-04 |  |  |  | 8/2: Data For Epic Metrics and CST have been loaded in Hbase and steps are documented in Monitoring Project - Data Collection and Storing steps
39 | Indexing Hbase content in Lily |  |  | Harish M | [7 empty] | 8/3: Lily index is created and was able to see the collection in Solr UI. Both me and muthu are yet to investigate on using the tool from here. Steps followed so far along with ref links are documented in Monitoring Project - Configurations and Installation Steps 8/2: Exploring the Lily indexing platform along with solr before creating indexing hbase content.expecting to be able to close it by EOD 3/8. Updates are added in Monitoring Project page as attachment.
40 | Automating data loading of Autosys job definitions |  |  | Anjana |  |  | 2017-08-04 | 2017-08-09
41 | Migrating Lens2 metrics to Kafka |  |  | Hareesh |  |  | 2017-08-04 | 2017-08-09
42 | Anomaly Detection – Rack level correlation based on CST tickets & anomalies in Epic data. |  |  | Hareesh |  |  | 2017-08-04 | 2017-08-09
43 | Deployment to ARA |  |  | Harish M |  |  | 2017-08-02 | 2017-08-08 |  |  |  | 2/8 Data For Epic Metrics and CST have been loaded in Hbase and steps are documented in Monitoring Project - Data Collection and Storing steps 4/8 API codes are loaded in the tomcat set up in ARA 7/8 There is an issue (persistent now and then) with the thrift server in ARA connecting to Hbase in 9090 and I have raised a ticket with DBA team for this :INC064699035
44 | Monitoring pipeline
45 | Slow Data Nodes |  |  | Gopal | In progress |  | 2017-08-04 | 2017-08-09 |  |  | Supervised Learning : Workflow/Job level anomalies using Supervised learning
46 | Store Oozie DAG in Hbase |  |  | Gopal | closed |  | 2017-08-04 | 2017-08-08 |  |  |  | Status - 08/08/2017 - COMPLETED
47 | ETLP | [10 empty] | To Confirm : Whether read data on-demand or replicate to HBase. Usecases to be identified. Prima facie, a simple on-demand API would suffice
48 | Install OpenTSDB |  |  | Harish M | [7 empty] | 8/7: Have raised INC064697639 ticket for installing dependencies with SE Linux team, as we needed root acess for a few tools which linux core dev tools. 8/4: Sujitha is having permission denied error and we are planning on going forward with a tar based approach to install dependencies. 8/3: Have shared the installation steps with Sujitha, to install and close it.
49 | Data replication setup between Oxpecker owned by DBA team to OepnTSDB in ARA |  |  | Gopal | In progress |  | 2017-08-05 | 2017-08-11

## ScopeChangeLog
Change ID # | Description | Schedule Impact? IF yes, effort hours | Budget Impact? If yes, amount | Resource Availabilty Impact? If yes, Resoures Names that have to be allocated/freedup | Notes
1
2
3
4
5

## Project Team Contact List
# | Resources | Wipro email id | Apple Network id | Apple Email id | Location | Primary Contact # | Role | Notes
1 | sandeep
2 | Hareesh Maturi
3 | Harish M
4 | Anjana
5 | Muthu
6 | Vidya Mohan
7 | Bharath
8 | Tejaswar Rao
9
10
11
12
13
14

## ValidValues
Log Item Type Valid Values | Notes
Action Item
Information
Issue
Key Decision Required (KDR) | KDR from and by date
Key Decision Made (KDM) | KDM by, effective from (Date) to (Date
Risk
Assumption

## Meeting Minutes
Sr | Date | Type of meeting | Attendees | Action Items | Status | Comments | Ownership
Open
[8 empty] | Closed | Anurag
[8 empty] | In Progress | Basant
[8 empty] | Pending confirmation | Sandeep
[8 empty] | Followup | Hareesh
[8 empty] | Yet to Start | Anjana
[8 empty] | N/A | Gopal
55 | 2017-03-03 | Daily | Alvaro John Tony Sandeep | Sandeep to include Mulesoft integration component in the Design approach and send it to Alvaro, Tony and John for their signoff by today eod. | Closed | 03/03:[SG]- HLD signoff received | Sandeep
56 | 2017-03-03 | Daily | Alvaro John Tony Sandeep | Mulesoft Integration API/ Interface will be provided by the Mulesoft Development team and Planview Development team will be responsible to integrate it in the existing Planview solution. Incase need be; the Mulesoft Development team would be available. | Closed | 03/03:[SG]- HLD signoff received | Sandeep
57 | 2017-03-03 | Daily | Alvaro John Tony Sandeep | Flow of the Data fetch from Planview UI would be 2 dimensional – either through Mulesoft as Plan A or through the NiFi as the Plan B. | Closed | 03/03:[SG]- HLD signoff received | Sandeep
58 | 2017-03-03 | Daily | Alvaro John Tony Sandeep | Rest of the Design flow is good and is signed off. | Closed | 03/03:[SG]- HLD signoff received | Sandeep
59 | 2017-03-03 | Daily | Alvaro John Tony Sandeep | Feasibility of Mulesoft integration in this Planview Project would be dependent on the Mulesoft development team turning over the working/compatible interface to be integrated in this Planview design flow and could be subject to a Change Request depending on its readiness and availability. | Closed | 03/03:[SG]- HLD signoff received | Sandeep
60 | 2017-03-03 | Daily | Alvaro John Tony Kathir Sandeep | Planview HLD sign off | Closed | 03/03:[SG]- HLD signoff received | Sandeep
61 | 2017-03-06 | Daily | Alvaro Sandeep | Descope the 2 CPS extracts from the Expense Outlook file and include the other 2 CPS extracts (Actual file and Commits file) in the scope | Closed | 03/06:[SG]- per Alvaro - descope the 2 CPS extracts from Expense Outlook file and include the 2 other CPS extracts - Actual file and Commits file | Sandeep
62 | 2017-03-06 | Daily | Alvaro John Tony Bala Sandeep | Share the Kellogg Tableau Development standards guide and Database Standards guide | Closed | 03/06:[SG] - Shared the Kellogg Development standards guide for both Database and Tableau | Sandeep
63 | 2017-03-07 | Daily | Alvaro Sandeep | Discuss the Project Scope with Grace | Closed | 03/07:[SG]- Grace confirmed, the Scope will be per the SOW - 11 data files in all - 8 Planview data files and 3 CPS extracts | Sandeep
64 | 2017-03-08 | Daily | Alvaro John Tony Bala Sandeep | Discuss and revisit the Project Architecture and Design | Closed | 03/08:[SG]- Discussed in detail the project architecture and design and requested signoff | Sandeep
65 | 2017-03-08 | Daily | Alvaro John Tony Sandeep | Project Planview scope redefined and finalized per the SOW limiting the total data-sets to 11 (8 data sets from Planview and 3 from Capital Planning System) | Closed | 03/08:[SG]- received revised(initial scope per SOW) HLD signoff | Sandeep
67 | 2017-03-08 | Daily | Alvaro John Tony Sandeep | Sandeep to update the Design document and send for signoff | Closed | 03/08:[SG]- Updated HLD signoff received by Tony and John 03/08:[SG]- Sandeep to share the updated HLD document for signoff | Sandeep

## Q&A
# | Questions | Raised by | Assigned To | Date Opened | Status | Last Update | Date Closed | Comments/Remarks
[9 empty] | Anurag | Open | Daily Meeting
[9 empty] | Basant | In Progress | Weekly Meeting
[9 empty] | Srini | Closed | Scope
[9 empty] | Gopal | Pending Clarification | Discussion
[9 empty] | Hareesh | Yet to Start | Action Item
[9 empty] | Anjana | N/A | Clarification
[9 empty] | Praveen |  | Issue
Santhosh
Sandeep
Muthu